## Main Analysis
Risk number | Capability | Undesirable event | Risk Description (Briefly describe what may happen if the Undesired event materializes. | Group member name who worked on the risk | Likelihood Score | Conseq Score | Risk Score | Net Score | Justification for the Likelihood score | Justification for the Consequence score | Mitigation (hardware, Hybrid, or software) | 1. Q1- What the system is supposed to do? "Desired Behavior" | 2. Q2- What the system is not supposed to do "Preventative Behavior" | 3. Q3- How the system will respond if there is an undesired condition "Responsive Behavior" | Functional requirements as per Q1 | Preventative requirements as per Q2 | Responsive requirements for Q3
R1 | Checkout & Order Placement | Race condition allows duplicate order submission | If two concurrent requests submit the same checkout session (e.g., the user double-clicks "Place Order", or the browser retries after a slow network response), the system may create two separate order records from a single cart. This causes incorrect inventory deduction and, if payment capture is tied to order creation, a potential duplicate charge to the customer. | Min Hsuan Wu | 3 | 4 | 3x4 | 12 | Rated 3 (Moderate) because double-submission from double-clicks or slow network retries is a common occurrence in web checkout flows, and the current implementation does not yet enforce an idempotency key across the full checkout request path. | Rated 4 (High) because a duplicate order causes incorrect inventory counts and a possible duplicate payment capture, directly affecting customer trust and financial reconciliation. | Software Mitigation. Generate a unique idempotency key per checkout session and require it on the order-creation request. Wrap order creation in a database transaction with a unique constraint on (CartId, IdempotencyKey). Disable the "Place Order" button immediately after the first click until a response is received. This mitigation reduces the likelihood of duplicate orders and lowers the risk from its current score. | The system shall accept exactly one order per completed checkout session, even if the checkout request is submitted more than once. | The system shall not create more than one order record for the same cart/session, and shall not process a second submission while the first is still being processed. | If a duplicate submission is detected, the system shall reject the duplicate request and return the existing order's confirmation instead of creating a new order. | FR-1.1: OrderService shall generate a unique idempotency key for each checkout session. FR-1.2: CheckoutController shall attach the idempotency key to every order-creation request. | FR-1.3: OrderRepository shall enforce a unique database constraint preventing two orders from being created with the same idempotency key. FR-1.4: CheckoutController shall disable resubmission while an order-creation transaction is in progress. | FR-1.5: CheckoutController shall detect a duplicate submission and return the existing order's confirmation page instead of creating a new order. FR-1.6: AuditLogger shall log every detected duplicate-submission attempt with cart ID and timestamp.
R2 | User Session Management | Session expires mid-checkout | If a user's authentication session expires while they are in the middle of checkout (entering shipping or payment details), the in-progress cart state may be lost, or a request may be processed against an invalid session context, causing the transaction to fail. | Min Hsuan Wu | 4 | 3 | 4x3 | 12 | Rated 4 (High) because checkout can take several minutes when a customer compares shipping options or looks up payment information, and the default ASP.NET Core Identity session/cookie timeout is short relative to that. | Rated 3 (Moderate) because the result is a failed transaction and a frustrated customer, but it does not corrupt data or expose a security vulnerability. | Software Mitigation. Persist cart contents to the database keyed by user ID rather than only in the session/cookie, so the cart survives session expiry. Use sliding expiration during active checkout. Prompt re-authentication without discarding the cart. | The system shall preserve the user's cart and checkout progress even if their authentication session expires during checkout. | The system shall not allow an order to be finalized using an expired or invalid authentication session. | If the session expires mid-checkout, the system shall prompt the user to re-authenticate and resume checkout with the cart intact, rather than discarding it. | FR-2.1: CartService shall persist cart contents to the database keyed by user ID, independent of session state. | FR-2.2: CheckoutController shall verify a valid, non-expired authentication token before finalizing any order. FR-2.3: PaymentService shall reject order-finalization requests carrying an expired session token. | FR-2.4: AuthenticationMiddleware shall redirect to re-login while preserving the return URL to the checkout page. FR-2.5: CartService shall restore the persisted cart automatically after successful re-authentication.
R3 | Admin Order Management (Version 2) | Privilege escalation on admin routes | If role-based authorization is not enforced correctly on the upcoming Admin Order Management Dashboard, a non-admin (customer) user could reach admin-only routes and view or modify other customers' orders, including changing order status without authorization. | Min Hsuan Wu | 1 | 5 | 1x5 | 5 | Rated 2 (Low) because ASP.NET Core's role-based [Authorize] attribute is a well-established mechanism, but the risk exists whenever a new controller or route is added and a role check is accidentally omitted or misconfigured. [Updated 2026-07-25] Likelihood reduced 2->1: role-based authorization is now enforced server-side ([Authorize(Roles="Admin")]) and roles are seeded, so the escalation path is closed for merged code. See PR #2 (e09f496). | Rated 5 (Severe) because a successful privilege escalation would expose all customers' order and personal data and allow unauthorized changes to order status — a severe confidentiality and integrity failure. | Software Mitigation. Enforce [Authorize(Roles="Admin")] at the controller level, not just by hiding UI elements client-side. Add automated integration tests asserting HTTP 403 responses for non-admin roles on every admin route. Centralize the authorization policy rather than relying on per-action checks. [Status 2026-07-25] IMPLEMENTED: [Authorize(Roles="Admin")] enforced at controller level (not UI-only) plus role seeding. Merged in PR #2. | The system shall allow only users with the Admin role to access order-management routes and to view or modify any customer's order. | The system shall not allow a non-admin, authenticated customer to reach admin order-management routes, even by direct URL access. | If a non-admin user attempts to access an admin route, the system shall deny the request, return an appropriate error, and log the attempt. | FR-3.1: AdminOrderController shall require the Admin role via [Authorize(Roles="Admin")] on every action. FR-3.2: AdminOrderService shall verify the caller's role server-side before returning or mutating any order. | FR-3.3: AuthorizationMiddleware shall reject any request to an /Admin/* route lacking the Admin role, regardless of client-side navigation state. FR-3.4: Automated integration tests shall assert that all admin routes return HTTP 403 for non-admin roles. | FR-3.5: AdminOrderController shall return HTTP 403 Forbidden for unauthorized access attempts. FR-3.6: AuditLogger shall record the user ID, attempted route, and timestamp for every denied admin-access attempt.
R4 | Order Status Lifecycle (Version 2) | Invalid order status transition | The planned order lifecycle (Pending → Processing → Shipped → Delivered) could be bypassed if the system does not validate transitions server-side, allowing an order to move to an invalid state (e.g., Delivered directly from Pending, or backward from Shipped to Pending), corrupting order history and the customer-facing status. | Min Hsuan Wu | 1 | 3 | 1x3 | 3 | Rated 3 (Moderate) because without an explicit server-side state machine, a direct API call or a UI bug could set an arbitrary status value. [Updated 2026-07-25] Likelihood reduced 3->1: a server-side transition state machine now rejects invalid order-status transitions, and OrderStatusTransitionTests.cs covers the allowed/blocked paths. See PR #2 (e09f496). | Rated 3 (Moderate) because the result is an inconsistent order record and customer-facing confusion, recoverable via manual admin correction, without exposing sensitive data. | Software Mitigation. Implement a server-side state machine that defines the allowed transitions and rejects any transition outside that set. Route all status changes through a single controlled service method rather than direct field writes. [Status 2026-07-25] IMPLEMENTED: server-side order-status state machine with transition validation + automated tests (OrderStatusTransitionTests.cs). Merged in PR #2. | The system shall allow an order's status to move only along the defined sequence: Pending → Processing → Shipped → Delivered. | The system shall not allow an order status to skip a required stage or move backward in the lifecycle. | If an invalid status transition is requested, the system shall reject the change, leave the order's current status unchanged, and notify the admin of the invalid attempt. | FR-4.1: OrderStatusService shall expose a single UpdateStatus method that is the only path for changing an order's status. FR-4.2: OrderStatusService shall validate the requested transition against a defined allowed-transitions table before applying it. | FR-4.3: OrderStatusService shall reject any transition not present in the allowed-transitions table. FR-4.4: AdminOrderController shall not permit direct writes to the OrderStatus field outside of OrderStatusService. | FR-4.5: AdminOrderController shall return a validation error describing why the transition was rejected. FR-4.6: AuditLogger shall record every rejected status-transition attempt with the attempted from/to states.
R5 | Admin & Role Management (Version 2) | Seeded admin account retained in production | Role/data seeding was introduced in PR #2 to create a baseline Admin role and account for development. If the seeding routine runs against a production database, or a known/default admin password is not rotated, an attacker (or a curious customer) could obtain full administrative access to order management, customer data, and order-status controls. | Min Hsuan Wu | 2 | 5 | 2x5 | 10 | Likelihood 2: seeding currently runs at application startup and is not yet gated by environment, but exploitation still requires the seeding to reach a production database and the default credential to remain unchanged. | Consequence 5: a live default admin account grants full control over orders, customers, and status transitions - effectively a total compromise of the application's trust boundary. | Software Mitigation. Gate role/data seeding behind an explicit environment check (Development/Test only); load the initial admin credential from protected secret/configuration storage instead of source code, and force rotation on first use; never seed a known default password in Production. | The system shall seed baseline roles/accounts only in non-production environments, and shall require production admin credentials to be provisioned through secure configuration. | The system shall not create or retain any account with a default or known password in a production environment. | If seeding is invoked in a production environment, the system shall abort the seeding operation and log a critical security event. | FR-5.1.1: SeedingModule shall execute role/user seeding only when the environment is Development or Test. FR-5.1.2: ConfigurationModule shall load the initial admin credential from protected secret storage rather than source code. | FR-5.2.1: SeedingModule shall reject execution when the environment is Production. FR-5.2.2: AccountModule shall not persist any user whose password matches a known default value. | FR-5.3.1: SeedingModule shall log a critical audit event and terminate startup if seeding is attempted in Production.
R6 | Build & Verification Pipeline (CI) | CI reports success without executing any tests | The CI workflow (.github/workflows/ci.yml) runs "dotnet test" with no project argument, so it resolves the root solution EComLite.sln. That solution registered only EComLite.Web and omitted EComLite.Tests, so the command matched zero test projects, exited 0, and reported a passing build. Every push and pull request therefore displayed a green check while none of the 34 automated tests actually ran. A regression - including one that breaks the order-status transition rules protecting R4 - could be merged with no signal. | Min Hsuan Wu | 1 | 4 | 1x4 | 4 | Likelihood 4: the condition was already active and undetected across multiple merges (CI was added in 61cd86a and PR #1/#2 both merged under a green check). Nothing in the pipeline surfaces an empty test run, so it persists silently until manually inspected. [Updated 2026-07-27] Likelihood reduced 4->1: EComLite.Tests is now registered in EComLite.sln, and a solution-level "dotnet test" (the exact command CI runs) discovers and executes the suite - verified locally with 34 passed / 0 failed. Consequence remains 4 because the pipeline still would not flag a future empty run. | Consequence 4: the project loses its automated safety net. Mitigations verified only by tests (notably R4 order status transition validation) become unenforced, and the green check actively creates false confidence, which is more damaging than having no CI at all. | Software Mitigation. Register EComLite.Tests in EComLite.sln so the solution-wide "dotnet test" discovers it. Additionally, treat an empty test run as a failure by asserting a minimum executed-test count, so a silently skipped suite can never present as a pass. [Status 2026-07-27] PARTIALLY IMPLEMENTED: EComLite.Tests added to EComLite.sln, so CI now executes all 34 tests. NOT YET IMPLEMENTED: the minimum executed-test-count assertion (FR-6.2.1) that would make an empty test run fail the build. | The system's CI pipeline shall execute the full automated test suite on every push and pull request, and shall report success only when all discovered tests have actually run and passed. | The CI pipeline shall not report a successful build when zero test projects were discovered or zero tests were executed. | If the pipeline discovers no test projects or executes no tests, it shall fail the run and report the empty discovery as the failure reason. | FR-6.1.1: SolutionConfiguration shall include every test project so that a solution-level test command discovers the full suite. FR-6.1.2: CIWorkflow shall execute the automated test suite on every push and pull request event. | FR-6.2.1: CIWorkflow shall reject a run outcome of "success" when the number of executed tests is zero. | FR-6.3.1: CIWorkflow shall fail the job and emit a diagnostic message identifying empty test discovery when no tests are executed.

## Weekly Log
Week | Week Of | Risk ID | Action | Prev Score (L x C = Net) | New Score (L x C = Net) | Change Summary / Rationale | Evidence
W1 | 2026-07-13 | R1 | Identified | - | 3 x 4 = 12 | Initial identification & scoring. Concurrent/double-submit at checkout can create duplicate orders. Mitigation (idempotency key) planned, not yet implemented. | Commit bef575f
W1 | 2026-07-13 | R2 | Identified | - | 4 x 3 = 12 | Initial identification. Auth session expiring mid-checkout may lose in-progress cart. Mitigation (DB-backed cart) planned. | Commit bef575f
W1 | 2026-07-13 | R3 | Identified | - | 2 x 5 = 10 | Initial identification. Privilege escalation on planned V2 admin routes. Mitigation planned (server-side role auth). | Commit bef575f
W1 | 2026-07-13 | R4 | Identified | - | 3 x 3 = 9 | Initial identification. Order status could skip the defined lifecycle if not validated server-side. Mitigation planned. | Commit bef575f
W2 | 2026-07-20 | R3 | Mitigation implemented / Re-scored | 2 x 5 = 10 | 1 x 5 = 5 | V2 delivered: [Authorize(Roles="Admin")] enforced at controller level + role seeding. Escalation path closed for merged code; likelihood 2 -> 1. Consequence unchanged (5). | PR #2 (e09f496)
W2 | 2026-07-20 | R4 | Mitigation implemented / Re-scored | 3 x 3 = 9 | 1 x 3 = 3 | V2 delivered: server-side order-status state machine + transition validation, with OrderStatusTransitionTests.cs covering allowed/blocked paths; likelihood 3 -> 1. | PR #2 (e09f496) + OrderStatusTransitionTests.cs
W2 | 2026-07-20 | R5 | Identified (new) | - | 2 x 5 = 10 | New risk surfaced by the role-seeding work: a seeded default admin account could persist into production if seeding is not environment-gated and the default credential is not rotated. | PR #2 (e09f496)
W2 | 2026-07-20 | R1 | Re-analyzed | 3 x 4 = 12 | 3 x 4 = 12 | Re-reviewed; still open. Idempotency-key mitigation not yet implemented. Remains a top-priority risk (tied highest score). | -
W2 | 2026-07-20 | R2 | Re-analyzed | 4 x 3 = 12 | 4 x 3 = 12 | Re-reviewed; still open. DB-backed cart persistence not yet implemented. Remains a top-priority risk. | -
W3 | 2026-07-27 | R1 | Re-analyzed (open) | 3 x 4 = 12 | 3 x 4 = 12 | Still highest-priority open risk. Next action: implement idempotency key on order-creation request. | -
W3 | 2026-07-27 | R2 | Re-analyzed (open) | 4 x 3 = 12 | 4 x 3 = 12 | Still open. Next action: persist cart to DB keyed by user ID. | -
W3 | 2026-07-27 | R5 | Re-analyzed (open) | 2 x 5 = 10 | 2 x 5 = 10 | Newly opened last week; mitigation (environment gate + secret-based admin credential) not yet implemented. Under monitoring. | -
W3 | 2026-07-27 | R6 | Identified (new) | - | 4 x 4 = 16 | New risk found while preparing to commit the V2 transition tests: CI ran "dotnet test" against EComLite.sln, which omitted EComLite.Tests, so all pushes passed green with zero tests executed. Highest-scoring open risk. | .github/workflows/ci.yml + EComLite.sln
W3 | 2026-07-27 | R6 | Mitigation implemented | 4 x 4 = 16 | 1 x 4 = 4 | EComLite.Tests registered in EComLite.sln; solution-level "dotnet test" now discovers and runs 34 tests (0 failed). Likelihood 4 -> 1; consequence unchanged. Residual: pipeline still would not flag a future empty run. | Verified locally: 34 passed, 0 failed
W3 | 2026-07-27 | - | No risks retired | - | - | No risks retired this week. R3, R4 and R6 remain tracked at reduced scores as regression guards even though their mitigations are implemented. | -